## User Stories
KEY | Initiative | Feature | Epic | As a | I want to | So that I can | Acceptance Criteria | Tasks | Sprint | Asignee | Status | JIRA
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a Hull to filter the ICAS trend data CMAS database query | export sensor data from only the specified Hull. | User can select a a single hull to query | Refactor GetSensorDataTableJson to query multiple ShipName entries | CMAS-AS FY20-004 | AT | In Process
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select specific sensors from a single ICAS trend from a single hull to filter the CMAS Database Query | export sensor data from specific sensors | User can select a sensor or sensors from a single ICAS trend from a single hull to query | Write the LINQ for selecting sensors from a single ICAS trend from a single Hull | CMAS-AS FY20-004 | TB | In Process
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select specific sensors from a single ICAS trend from a single hull to filter the CMAS Database Query | export sensor data from specific sensors | User can select a sensor or sensors from a single ICAS trend from a single hull to query | Create New API Route to Serve Data | CMAS-AS FY20-004 | TB | In Process
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a single Hull to filter the CMAS database query | export sensor data from only the specified Hull. | User can select a a single hull to query | Write the LINQ for selecting Single Hull |  |  | Backlog | DAU-542
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a Hull to filter the ICAS trend data CMAS database query | export sensor data from only the specified Hull. | User can select a a single hull to query | Create New API Route to Serve Data |  |  | Backlog | DAU-542
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select specific sensors from multiple ICAS trends from a single hull to filter the CMAS Database Query | export sensor data from sensors in different trends on the same hull simultaneously. | User can select multiple sensors from two or more ICAS trends on a single hull to query | Write the LINQ for selecting multiple sensors from different ICAS trends on a single hull
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select specific sensors from multiple ICAS trends from a single hull to filter the CMAS Database Query | export sensor data from sensors in different trends on the same hull simultaneously. | User can select multiple sensors from two or more ICAS trends on a single hull to query | Create New API Route to Serve Data
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select the same ICAS trend from multiple hulls to filter the CMAS database query | export the same trend from multiple hulls simultaneously | User can select an ICAS trend from two or more hulls to query | Write the LINQ for selecting a single trend from multiple hulls
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select the same ICAS trend from multiple hulls to filter the CMAS database query | export the same trend from multiple hulls simultaneously | User can select an ICAS trend from two or more hulls to query | Create New API Route to Serve Data
| CMAS API Services | Database Interface | Get ICAS Log Data | Data Scientist | select an ICAS eLOG to filter the CMAS Database Query | export sensor data from ICAS eLOG on single hull | User can select specific ICAS eLOG to query for export. | Write the LINQ for selecting ICAS eLOG from Single Hull |  |  | Backlog | DAU-543
| CMAS API Services | Database Interface | Get ICAS Log Data | Data Scientist | select an ICAS eLOG to filter the CMAS Database Query | export sensor data from ICAS eLOG on single hull | User can select specific ICAS eLOG to query for export. | Create New API Route to Serve Data |  |  |  | DAU-543
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a Date and Time range to filter CMAS database query | export sensor data from a specified time period | User can select Date and Time Range to query | Write the LINQ for selecting Data and Time Ranges | CMAS-AS FY20-001 | TB | Complete | DAU-536
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a Date and Time range to filter CMAS database query | export sensor data from a specified time period | User can select Date and Time Range to query | Create New API Route to Serve Data | CMAS-AS FY20-003 | TB | Complete | DAU-536
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a Hull to filter the ICAS trend data CMAS database query | export sensor data from only the specified Hull. | User can select a a single hull to query | Compare and document differences between GetSensorDataTable and GetSensorDataTableJson | CMAS-AS FY20-003 | AT | Complete
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a single ICAS Trend from a single hull to filter the CMAS Database Query | export sensor data from a single ICAS trend | User can select a single ICAS Trend from a hull to query. | Write the LINQ for selecting Single ICAS Trend from Single Hull | CMAS-AS FY20-003 | TB | Complete | DAU-543
| CMAS API Services | Database Interface | Get ICAS Trend Data | Data Scientist | select a single ICAS Trend from a single hull to filter the CMAS Database Query | export sensor data from a single ICAS trend | User can select a single ICAS Trend from a single hull to query. | Create New API Route to Serve Data | CMAS-AS FY20-003 | TB | Complete | DAU-543
| CMAS API Services | Server-side API Endpoint | Metrics and Logging | Database Administrator | automate calculation of time it takes for API to return queried data | Track API performance | API returns duration it takes for requested data to be returned for each request |  |  |  | Backlog
| CMAS API Services | Server-side API Endpoint | Metrics and Logging | Database Administrator | automate logging of 'who', 'when', and 'how long' when database gets queried using the API | Track users and API performance | Database admin can access automated log containing user, timestamp and duration of each event when API was used |  |  |  | Backlog
| CMAS-AS ETL Services | Data Transform Stack | Architecture Design | Software Architect | survery open source technologies that could be used to perform ETL, Client-side APIs, Data Cache, and work flow management | design CMAS-AS ETL Services | Proposed software frameworks for CMAS ETL Services. Suggested options for in house development or use of open source tools to perform ETL, Client-side APIs, Data Cache, and work flow management | Survey Python- and Apache-based open source technologies. | CMAS-AS FY20-004 | MD | In Process
| CMAS-AS ETL Services | Data Transform Stack | Architecture Design | Software Architect | survey open source technologies that could be used to perform ETL, Client-side APIs, Data Cache, and work flow management | design CMAS-AS ETL Services | Proposed software frameworks for CMAS ETL Services. Suggested options for in house development or use of open source tools to perform ETL, Client-side APIs, Data Cache, and work flow management | Develop initital framework suggestions based on Python- and Apache-based open source technologies survey. | CMAS-AS FY20-004 | MD | In Process
| CMAS API Services | Database Interface | Get eRM Historian | [7 empty] | Backlog
| CMAS API Services | Database Interface | Get ICAS Event Data
| CMAS API Services | Database Interface | Get 3M OARS Data
| CMAS API Services | Database Interface | Put Calculated Data
| CMAS API Services | Database Interface | Post Calculated Data
| CMAS API Services | Server-side API Endpoint | Request Management
| CMAS-AS ETL Services | Client-side API Endpoint | Automated Data Queries
| CMAS-AS ETL Services | Data Cache
| CMAS-AS Cloud Migration | CMAS Analytics App
| CMAS-AS Cloud Migration | Migrate ETL Services
| CMAS-AS Cloud Migration | Machine Learning Stack